## Sheet1
Burn Down Chart / Sprint and Backlog
ID | Task Name | Duration | Start | Finish | August/ September |  |  | September |  | September | September
[5 empty] | 1st Three Days | 2nd Three Days | 1st Three Days | Two Days | Three Days | 3rd Sprint | 4th Sprint
1
2 | Understanding | 3 Days | 26/08/19 | 27/08/19
3 | Requirements gathering | 3 Days | 28/08/19 | 30/08/19
4 | Python Programing and Development | 3 Days | 01/09/19 | 03/09/19
5 | Visualization | 2 Days | 04/09/19 | 05/09/19
6 | Features Engineering | 3 Days | 06/09/19 | 08/09/19
7 | Training and testing | 3 Days | 09/08/19 | 11/08/19
8 | Version Control with Git | 2 Days | 12/08/19 | 13/08/19

## Sheet7
1
Visualize the data with activity , Accelerometer and Gyroscopr
Load Dataset
Visualize the Data after Low Pass Filter
2
3
Feature Engineering
with Accelerometer and Gyroscope Data and save Training data after splitting
4
5
Define Model with KNN and SVM Build, Fir,Train and Test the Model
Sprint-1
Sprint-3
Sprint-1